KỂ HOẠCH TUYỂN SINH 2026 - V11

Enrollment Operating System

Trường Việt Anh | 2026

# GIỚI THIỆU & TỔNG QUAN

Tài liệu này định nghĩa "Enrollment Operating System" hoàn chỉnh cho mùa tuyển sinh 2026 của Trường Việt Anh, bao gồm 19 chương chi tiết trên 5 phần chính.

PHẦN A: Nền Tảng (Personas, Funnel, SLA, SOP)

PHẦN B: Kênh & Ngân Sách (4 trục kênh, 10.8 tỷ committed)

PHẦN C: Vận Hành Hàng Ngày (Dashboard, Weekly Battleplan)

PHẦN D: Công Nghệ (CRM, Analytics, Landing Pages)

PHẦN E: Kiểm Soát & Cải Tiến (QA, Lost Tracking, Training)

Mục tiêu: 1,300 học sinh, 13 tỷ VND, 28 tuần (26/03 - 30/09/2026), CAC < 10M/student

# MỤC LỤC

PHẦN A - NỀN TẢNG HỆ THỐNG

Chương 1: Tổng Quan Enrollment Operating System

Chương 2: Chân Dung Khách Hàng (4 Personas)

Chương 3: Funnel 8 Tầng

Chương 4: SLA Tuyển Sinh

Chương 5: SOP School Tour

PHẦN B - CẤU TRÚC KÊNH & NGÂN SÁCH

Chương 6: Cấu Trúc Kênh 4 Trục

Chương 7: Budget Governance

Chương 8: Chi Tiết Paid Media

PHẦN C - VẬN HÀNH HÀNG NGÀY

Chương 9: Dashboard 12 Số

Chương 10: Weekly Battleplan

Chương 11: Campus Ownership

Chương 12: Content Engine

PHẦN D - CÔNG NGHỆ & TRACKING

Chương 13: CRM Kép (GHL + Pancake)

Chương 14: Landing Pages & Funnels

Chương 15: Analytics & GTM

PHẦN E - KIỂM SOÁT & CẢI TIẾN

Chương 16: QA & Mystery Call

Chương 17: Lost Reasons Tracking

Chương 18: Offer & Deadline Management

Chương 19: Nhân Sự & Đào Tạo

# PHẦN A - NỀN TẢNG HỆ THỐNG

# Chương 1: Tổng Quan Enrollment Operating System

## 1.0 Định Nghĩa & Tầm Nhìn

Enrollment Operating System (EOS) là tập hợp các quy trình, người, công nghệ, và dữ liệu được tối ưu hóa để đạt mục tiêu tuyển sinh một cách hiệu quả, có trách nhiệm, và sustainable.

## 1.1 KPI Tổng Thể

| Chỉ Tiêu | Mục Tiêu | Ghi Chú |
| --- | --- | --- |
| Học sinh tuyển sinh | 1,300 | Tất cả 6 campus, 4 cấp học |
| Ngân sách tổng | 13 tỷ VND | 10.8 committed + 2.2 linh hoạt |
| Timeline | 28 tuần | 26/03 - 30/09/2026 |
| CAC (avg) | < 10M VND | Điều chỉnh theo cấp học |
| Lead volume cần | ~15,080 | Dựa trên funnel benchmarks |
| Conversion rate | 4.5% | Từ lead mới → enrolled |

## 1.2 Timeline 4 Giai Đoạn

| Giai Đoạn | Khoảng | Tuần | Budget % | Focus Chính |
| --- | --- | --- | --- | --- |
| Warm-up | 26/03-30/04 | 8 | 18.5% | Brand awareness, setup |
| Ramp-up | 01/05-30/06 | 8 | 32.4% | Lead scaling, offer test |
| Peak | 01/07-31/08 | 8 | 37.0% | Aggressive campaigns |
| Close | 01/09-30/09 | 4 | 12.0% | Last-minute offers |

## 1.3 20 Quyết Định Lock Trong 72h Đầu

1. Budget approval (10.8 tỷ)

2. Budget allocation by stage/channel/campus

3. Landing page roadmap & deadlines

4. Google Ads keywords list (150+)

5. Creative assets uploaded & approved

6. Influencer partnerships confirmed

7. Campus leads assigned

8. Admissions team training schedule

9. Open Day dates & agendas

10. Webinar topics & speakers

11. Telesales scripts approved

12. CRM workflows setup & tested

13. Make.com sync tested & live

14. Analytics setup (25 GTM tags)

15. Remarketing audiences created

16. Email sequences written

17. SMS templates finalized

18. Zalo OA content pre-loaded

19. Mystery call process defined

20. Weekly meeting calendar blocked

# Chương 2: Chân Dung Khách Hàng (4 Personas)

## 2.1 Persona 1: Ba Mẹ Mầm Non (25-35)

| Khía Cạnh | Chi Tiết |
| --- | --- |
| Tuổi con | 2-5 |
| Học vấn | Đại học+ (70%) |
| Thu nhập | 15-40M/tháng |
| Pain points | Giáo dục sớm, tiếng Anh, bạn bè |
| Decision time | 30-45 ngày |
| Decision factors | Curriculum 40%, facilities 30%, price 20%, convenience 10% |
| Info sources | Facebook, Google, word-of-mouth |
| Geographic | Gò Vấp 40%, Bình Tân 35%, Tây Ninh 25% |

## 2.2 Persona 2: Ba Mẹ Tiểu Học (30-40)

Độ tuổi con: 6-11. Trình độ: Đại học-Cao học (75%). Thu nhập: 20-50M. Pain points: Tiếng Anh + Toán, extra-curricular. Decision time: 45-60 ngày. Focus: Academic reputation 35%, teacher quality 25%.

## 2.3 Persona 3: Ba Mẹ Cấp 2 (35-45)

Độ tuổi con: 12-14. Trình độ: Cao học (60%, entrepreneurs). Thu nhập: 30-60M+. Pain points: Academic excellence, university prep, character. Decision time: 60-75 ngày. Focus: Curriculum 40%, university prep 30%.

## 2.4 Persona 4: Ba Mẹ Cấp 3 (38-50)

Độ tuổi con: 15-18. Trình độ: Cao học (70%, executives). Thu nhập: 40-80M+. Pain points: UniversitySuccess, international pathways. Decision time: 75-90+ ngày. Focus: International pathways 40%, outcomes 30%.

# Chương 3: Funnel 8 Tầng - Pipeline Tuyển Sinh

## 3.1 Định Nghĩa Các Tầng

New Lead: Chưa contact

Contacted: Có phản hồi

Qualified: Xác nhận nhu cầu & timeline

Booked Tour: Đặt hẹn (confirmation sent)

Showed Tour: Đã tham quan

Offer: Tư vấn viên đã đưa quote

Deposit: Thanh toán tiền nạp

Enrolled: Hoàn tất enrollment

## 3.2 Conversion Benchmarks

| Transition | Target % | Meaning |
| --- | --- | --- |
| Lead → Contacted | 90% | 9/10 contacted |
| Contacted → Qualified | 60% | 6/10 qualified |
| Qualified → Booked | 50% | 5/10 book tour |
| Booked → Showed | 70% | 7/10 show up |
| Showed → Offer | 80% | 8/10 get offer |
| Offer → Deposit | 60% | 6/10 convert |
| Deposit → Enrolled | 95% | 95% complete |

## 3.3 Pipeline Math

Để đạt 1,300 enrolled:

1,300 enrolled ÷ 95% = 1,368 deposits

1,368 ÷ 60% = 2,280 offers

2,280 ÷ 80% = 2,850 showed

2,850 ÷ 70% = 4,071 booked

4,071 ÷ 50% = 8,143 qualified

8,143 ÷ 60% = 13,572 contacted

13,572 ÷ 90% = 15,080 leads

Cần ~15,080 fresh leads để đạt mục tiêu

# Chương 4: SLA Tuyển Sinh - Cam Kết Dịch Vụ

## 4.1 Response Time Targets

| Source | Trong Giờ | Ngoài Giờ |
| --- | --- | --- |
| Facebook Lead | 3 phút | 15 phút |
| Google Lead | 5 phút | 20 phút |
| Walk-in | 2 phút | N/A |
| Phone | < 1 phút | < 15 phút |
| Email | 2 giờ | 4 giờ |

## 4.2 8-10 Touchpoints trong 7 Ngày

TP1: Initial contact

TP2-3: Nurture messages

TP4: Book tour

TP5: Pre-tour reminder

TP6: Tour

TP7: Post-tour follow-up

TP8-10: Offer + deadline

## 4.3 No-Show Recovery

Step 1: Call within 30 min of no-show

Step 2: Offer 2 reschedule times

Step 3: Virtual tour if needed

Step 4: Move to recovery campaign if 2x miss

## 4.4 SLA Escalation

1 violation: Manager conversation

2-3 violations: Team lead coaching

4+ violations: PIP or role change

# Chương 5: SOP School Tour (75 Phút)

## 5.1 Timeline Cấu Trúc

| Segment | Time | Objective |
| --- | --- | --- |
| Đón Tiếp | 10m | Build rapport, discover needs |
| Presentation | 15m | Value proposition |
| Tour | 25m | Show campus |
| Q&A | 15m | Address objections |
| Offer & Close | 10m | Pricing, urgency, next step |

## 5.2 Segment Details & Scripts

Segment 1 (10m): "Chào mừng gia đình. Tôi là [Name]. Xin mời ngồi cà phê. Hôm nay gia đình quan tâm cấp nào?" [Take notes]

Segment 2 (15m): Present curriculum, outcomes, unique features. Use visuals.

Segment 3 (25m): Show classrooms, labs, sports, cafeteria. Take photos. Highlight quality.

Segment 4 (15m): Q&A on price, location, academic, discipline. Handle objections.

Segment 5 (10m): "Early bird 15% off, valid đến [DATE]. Only 8 spots left. Confirm deposit hôm nay?"

## 5.3 Pre-Tour Checklist

Campus clean & organized

Students notified

Teachers briefed

Brochures printed

Coffee ready

Parking cleared

CRM lead info pulled

Staff appearance professional

## 5.4 Objection Handling Playbook

"Giá cao" → "Premium quality, international standard, teacher credentials top 10%. Education is long-term investment."

"Xa" → "Shuttle services from [areas]. 7-8am pickup, 3:30pm dropoff. Carpools available."

"Chưa quyết định" → "Compare other schools. Early bird discount expires [DATE]. Only [X] spots left."

# PHẦN B - CẤU TRÚC KÊNH & NGÂN SÁCH

# Chương 6: Cấu Trúc Kênh 4 Trục

## 6.1 Trục 1 - Intent Capture (30% budget)

Google Search Ads: 150+ keywords

Google Display: Education sites

YouTube Pre-roll: Education channels

SEO: Organic optimization

KPI: CPL < 1M, CTR > 3%, Conv > 8%

## 6.2 Trục 2 - Demand Creation (35% budget)

Facebook/Instagram: Awareness videos

TikTok: Viral content

Zalo: Community targeting

KPI: CPM < 20K, Reach 500K+, Engagement > 2%

## 6.3 Trục 3 - Nurture (20% budget)

Email: Welcome, value, objections, deadline

SMS: Reminders & urgency

Zalo OA: Rich media support

Retargeting: Dynamic ads

KPI: Open > 25%, Click > 5%

## 6.4 Trục 4 - Conversion (15% budget)

School Tour: Scheduled visits

Open Day: Large events

Webinar: Expert talks

Telesales: 1-1 closing

KPI: Tour→Offer 80%, Offer→Deposit 60%

# Chương 7: Budget Governance

| Giai Đoạn | Khoảng | Budget | % | Action |
| --- | --- | --- | --- | --- |
| Warm-up | 26/03-30/04 | 2.0T | 18.5% | Setup, awareness |
| Ramp-up | 01/05-30/06 | 3.5T | 32.4% | Lead scaling |
| Peak | 01/07-31/08 | 4.0T | 37.0% | Max spend |
| Close | 01/09-30/09 | 1.3T | 12.0% | Last offers |

Flexible budget (2.2T) released per performance: channels hitting CAC target get +20% allocation

# Chương 8: Chi Tiết Paid Media Theo Kênh

## 8.1 Google Ads: 150+ Keywords, Display, YouTube, Perf Max

## 8.2 Meta: Lead Ads, Video, Carousel, Retargeting

## 8.3 TikTok: Spark Ads, In-feed, Hashtag Challenges

## 8.4 Zalo: OA Followers, Conversion Ads

# PHẦN C - VẬN HÀNH HÀNG NGÀY

# Chương 9: Dashboard 12 Số Hàng Ngày

| # | Metric | Target | Red Alert |
| --- | --- | --- | --- |
| 1 | Spend/day | ~40M | > 50M |
| 2 | New Leads | ~40 | < 25 |
| 3 | Qualified | ~24 | < 15 |
| 4 | CPL | < 300K | > 400K |
| 5 | Response Time | < 5m | > 10m |
| 6 | Tours Booked | ~10 | < 5 |
| 7 | Show-up Rate % | > 70% | < 50% |
| 8 | Offers Made | ~8 | < 4 |
| 9 | Deposits | ~4 | < 2 |
| 10 | Enrollments | ~2 | < 1 |
| 11 | CAC (avg) | < 10M | > 12M |
| 12 | Forecast Gap | Weekly | > 10% |

# Chương 10: Weekly Battleplan - 5 Phases

Phase 1 (Mon 9am): Data review - review metrics, identify issues, create action list

Phase 2 (Tue 2pm): Optimization - adjust Google Ads, Meta, landing pages

Phase 3 (Wed 10am): Pipeline review - check every lead in GHL, move along

Phase 4 (Thu 2pm): Content launch - approve creatives, schedule campaigns

Phase 5 (Fri 3pm): Planning - forecast next week, budget check, staffing

# Chương 11-19: Các Chương Còn Lại (Tóm Tắt)

Ch11: Campus Ownership & RACI - mỗi campus lead chịu trách nhiệm KPI cuối cùng

Ch12: Content Engine - content mapped to funnel stages (TOFU/MOFU/BOFU)

Ch13: CRM Kép (GHL + Pancake) - pipeline mgmt + social chat consolidation

Ch14: Landing Pages (24 funnels) - optimized per grade/season/offer

Ch15: Analytics & GTM - 25 tags, CAPI, remarketing audiences

Ch16: QA & Mystery Call - monthly mystery calls, scoring rubric, coaching

Ch17: Lost Reasons - tag every lost lead, monthly analysis, win-back campaigns

Ch18: Offer & Deadline - pricing tiers, urgency tools, deposit collection

Ch19: Nhân Sự & Training - 16-18 FTE team, pre-launch + monthly training

# KẾT LUẬN

Kế hoạch tuyển sinh 2026 phiên bản 11 biến đổi từ "marketing plan" sang "enrollment operating system" với 19 chương chi tiết, 5 phần cấu trúc.

Mục tiêu: 1,300 học sinh, 13 tỷ VND, 28 tuần, CAC < 10M/student.

Phương pháp: 8-tầng funnel, 4-trục kênh, SLA chặt, QA liên tục. Mỗi lead tracked, mỗi stage có benchmark, mỗi loss analyzed.

Bắt đầu: 26/03/2026. Lock 20 decisions trong 72h. Chạy hàng tuần theo 5-phase battleplan. Track 12 metrics daily. Cải tiến liên tục. Enroll 1,300 students by 30/09/2026.